## Sheet1
[8 empty] | 2024-01-15 |  |  |  | 2024-02-12 |  |  |  | 2024-03-11 |  |  |  | 2024-04-08
| Project Start Date: | 2024-01-08 | Project End Date: |  | 2024-04-01 |  |  | 2024-01-15 |  |  |  | 2024-02-12 |  |  |  | 2024-03-11 |  |  |  | 2024-04-08
| Project Name: | UON Course Planner Project | Group: | #3 (BIT) |  |  | Week Starting: | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22
# | Activity | Assigned To | Start | End | Days | Status | %Done
Sprint 1
1 | Establish Comm Channels | All | 2024-01-08 | 2024-01-09 | 2 | Complete | 100% | bar: 2024-01-08
2 | Compile Course Data | Diing Yang | 2024-01-08 | 2024-01-09 | 2 | Complete | 100% | bar: 2024-01-08
3 | Conduct Feasibility Study | All | 2024-01-08 | 2024-01-15 | 6 | Complete | 100% | bar: 2024-01-15
4 | Gather Requirements | All | 2024-01-08 | 2024-01-15 | 6 | Complete | 100% | bar: 2024-01-15
5 | Perform System Analysis | All | 2024-01-08 | 2024-01-29 | 16 | Complete | 100% | bar: 2024-01-29
6 | Complete Pre-Action Plan | Li Yang, Marcus | 2024-01-15 | 2024-01-16 | 2 | Complete | 100% | bar: 2024-01-15
7 | Write Project Plan | Marcus, Kennedy | 2024-01-15 | 2024-02-08 | 19 | Complete | 100% | bar: 2024-02-05
8 | Create product backlog | Li Yang, Marcus | 2024-01-15 | 2024-01-22 | 6 | Complete | 100% | bar: 2024-01-22
9 | Design use case diagram | Kennedy, An, Suhain | 2024-01-15 | 2024-01-22 | 6 | Complete | 100% | bar: 2024-01-22
10 | Write Business Rules | Diing Yang, Suhain | 2024-01-15 | 2024-02-05 | 16 | Complete | 100% | bar: 2024-02-05
11 | Design UI | Kennedy, An, Suhain, Diing Yang | 2024-01-15 | 2024-02-05 | 16 | Complete | 100% | bar: 2024-02-05
12 | Write Use Case Description | All | 2024-01-29 | 2024-03-23 | 40 | Complete | 100% | bar: 2024-03-18
Sprint 2
13 | Update UI Design | All | 2024-02-05 | 2024-03-20 | 33 | Complete | 100% | bar: 2024-03-18
14 | Design activity diagram | All | 2024-02-05 | 2024-02-27 | 17 | Complete | 100% | bar: 2024-02-26
15 | Create GitHub Repository | Marcus | 2024-02-24 | 2024-02-26 | 1 | Complete | 100% | bar: 2024-02-26
16 | Learn Node.js | Li Yang, Marcus, Diing Yang | 2024-02-26 | 2024-03-10 | 10 | Complete | 100% | bar: 2024-03-04
17 | Learn React | Li Yang, Marcus, Diing Yang | 2024-02-26 | 2024-03-10 | 10 | Complete | 100% | bar: 2024-03-04
18 | Write Report | All | 2024-02-26 | 2024-03-31 | 25 | Complete | 100% | bar: 2024-03-25
19 | Complete Presentation Slides | All | 2024-02-26 | 2024-03-31 | 25 | Complete | 100% | bar: 2024-03-25
| Statuses |  |  | FALSE
| Not started |  |  | TRUE
| In progress |  |  | TRUE
| Complete |  |  | TRUE
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))
Days = IF([End, row below]="","",NETWORKDAYS([Start, row below],[End, row below]))